## Overview
KUTMB HR ¦ SYSTEM CORE TRACEABILITY
v0.3 DRAFT ¦ 29 October 2026 ¦ github.com/harishaikal940322/kutmb-hr
MEASURE | COUNT | STATE
Modules (registered) | 11 | DRAFT / mixed
System Core modules | 3 | Priority: MOD-001
HR Core modules | 8 | HOLD / out of scope
Requirements | 32 | 0 approved
Open MOD-001 decisions | 12 | Awaiting IT / HR
Change Requests | 0 | No scope CR
CURRENT DEVELOPMENT BOUNDARY
MOD-001 User Management first ¦ MOD-002/003 supporting ¦ MOD-004..011 HR CORE ON HOLD
All requirements DRAFT. No HR requirement, implementation gate or test has been approved.

## Modules
Module ID | Module Name | Feature ID(s) | Layer | Lifecycle Status | Phase | SRS / Doc
MOD-001 | User Management & Identity Access | F-001,F-002,F-003,F-004 | SYSTEM CORE | DRAFT - PRIORITY 1 (SRS REVIEW) | P1-A | DOC-005
MOD-002 | System Configuration & Reference Data | F-005,F-006 | SYSTEM CORE | DRAFT - SUPPORTING / SCOPE REVIEW | P1-B | DOC-006
MOD-003 | Security Audit & Platform Reliability | F-007,F-008 | SYSTEM CORE | DRAFT - CROSS-CUTTING / SUPPORTING | P1-A/P1-C | DOC-004
MOD-004 | Employee & Organization | F-009 | HR CORE | HOLD - AWAIT HR REQUIREMENTS | P2+ HOLD | DOC-007 (reserved)
MOD-005 | Leave Management | F-010 | HR CORE | OUT OF SCOPE - AWAIT HR REQUIREMENTS | P2+ HOLD | TBD
MOD-006 | Attendance Management | F-010 | HR CORE | OUT OF SCOPE - AWAIT HR REQUIREMENTS | P2+ HOLD | TBD
MOD-007 | Overtime Management | F-010 | HR CORE | OUT OF SCOPE - AWAIT HR REQUIREMENTS | P2+ HOLD | TBD
MOD-008 | Payroll | F-010 | HR CORE | OUT OF SCOPE - AWAIT HR REQUIREMENTS | P2+ HOLD | TBD
MOD-009 | Claims | F-010 | HR CORE | OUT OF SCOPE - AWAIT HR REQUIREMENTS | P2+ HOLD | TBD
MOD-010 | Performance Review | F-010 | HR CORE | OUT OF SCOPE - AWAIT HR REQUIREMENTS | P2+ HOLD | TBD
MOD-011 | HR Approval Workflows | F-010 | HR CORE | OUT OF SCOPE - AWAIT HR REQUIREMENTS | P2+ HOLD | TBD

## RTM
Requirement ID | Module ID | Feature ID | AC ID | Test ID | Doc ID | Lifecycle | Test Evidence | Last CR ID
SYS-BR-001 | MOD-001 | F-001 | AC-SYS-BR-001 | T-SYS-BR-001 | DOC-004 | DRAFT | NOT TESTED
SYS-DR-001 | MOD-001 | F-004 | AC-SYS-DR-001 | T-SYS-DR-001 | DOC-004 | DRAFT | NOT TESTED
SYS-SEC-001 | MOD-003 | F-007 | AC-SYS-SEC-001 | T-SYS-SEC-001 | DOC-004 | DRAFT | NOT TESTED
SYS-SEC-002 | MOD-003 | F-007 | AC-SYS-SEC-002 | T-SYS-SEC-002 | DOC-004 | DRAFT | NOT TESTED
SYS-AUD-001 | MOD-003 | F-007 | AC-SYS-AUD-001 | T-SYS-AUD-001 | DOC-004 | DRAFT | NOT TESTED
SYS-NFR-001 | MOD-003 | F-008 | AC-SYS-NFR-001 | T-SYS-NFR-001 | DOC-004 | DRAFT | NOT TESTED
SYS-NFR-002 | MOD-003 | F-008 | AC-SYS-NFR-002 | T-SYS-NFR-002 | DOC-004 | DRAFT | NOT TESTED
SYS-ERR-001 | MOD-003 | F-007 | AC-SYS-ERR-001 | T-SYS-ERR-001 | DOC-004 | DRAFT | NOT TESTED
SYS-CFG-001 | MOD-002 | F-005 | AC-SYS-CFG-001 | T-SYS-CFG-001 | DOC-004 | DRAFT | NOT TESTED
IAM-FR-001 | MOD-001 | F-001 | AC-IAM-FR-001 | T-IAM-FR-001 | DOC-005 | DRAFT | NOT TESTED
IAM-FR-002 | MOD-001 | F-001 | AC-IAM-FR-002 | T-IAM-FR-002 | DOC-005 | DRAFT | NOT TESTED
IAM-FR-003 | MOD-001 | F-001 | AC-IAM-FR-003 | T-IAM-FR-003 | DOC-005 | DRAFT | NOT TESTED
IAM-FR-004 | MOD-001 | F-003 | AC-IAM-FR-004 | T-IAM-FR-004 | DOC-005 | DRAFT | NOT TESTED
IAM-FR-005 | MOD-001 | F-003 | AC-IAM-FR-005 | T-IAM-FR-005 | DOC-005 | DRAFT | NOT TESTED
IAM-FR-006 | MOD-001 | F-002 | AC-IAM-FR-006 | T-IAM-FR-006 | DOC-005 | DRAFT | NOT TESTED
IAM-FR-007 | MOD-001 | F-002 | AC-IAM-FR-007 | T-IAM-FR-007 | DOC-005 | DRAFT | NOT TESTED
IAM-FR-008 | MOD-001 | F-001 | AC-IAM-FR-008 | T-IAM-FR-008 | DOC-005 | DRAFT | NOT TESTED
IAM-FR-009 | MOD-001 | F-003 | AC-IAM-FR-009 | T-IAM-FR-009 | DOC-005 | DRAFT | NOT TESTED
IAM-FR-010 | MOD-001 | F-002 | AC-IAM-FR-010 | T-IAM-FR-010 | DOC-005 | DRAFT | NOT TESTED
IAM-FR-011 | MOD-001 | F-001 | AC-IAM-FR-011 | T-IAM-FR-011 | DOC-005 | DRAFT | NOT TESTED
IAM-FR-012 | MOD-001 | F-001 | AC-IAM-FR-012 | T-IAM-FR-012 | DOC-005 | DRAFT | NOT TESTED
IAM-AUD-001 | MOD-003 | F-007 | AC-IAM-AUD-001 | T-IAM-AUD-001 | DOC-005 | DRAFT | NOT TESTED
CFG-FR-001 | MOD-002 | F-005 | AC-CFG-FR-001 | T-CFG-FR-001 | DOC-006 | DRAFT | NOT TESTED
CFG-FR-002 | MOD-002 | F-006 | AC-CFG-FR-002 | T-CFG-FR-002 | DOC-006 | DRAFT | NOT TESTED
CFG-FR-003 | MOD-002 | F-006 | AC-CFG-FR-003 | T-CFG-FR-003 | DOC-006 | DRAFT | NOT TESTED
CFG-FR-004 | MOD-002 | F-006 | AC-CFG-FR-004 | T-CFG-FR-004 | DOC-006 | DRAFT | NOT TESTED
CFG-FR-005 | MOD-002 | F-006 | AC-CFG-FR-005 | T-CFG-FR-005 | DOC-006 | DRAFT | NOT TESTED
CFG-FR-006 | MOD-002 | F-006 | AC-CFG-FR-006 | T-CFG-FR-006 | DOC-006 | DRAFT | NOT TESTED
CFG-FR-007 | MOD-002 | F-005 | AC-CFG-FR-007 | T-CFG-FR-007 | DOC-006 | DRAFT | NOT TESTED
CFG-FR-008 | MOD-002 | F-005 | AC-CFG-FR-008 | T-CFG-FR-008 | DOC-006 | DRAFT | NOT TESTED
CFG-DR-001 | MOD-002 | F-006 | AC-CFG-DR-001 | T-CFG-DR-001 | DOC-006 | DRAFT | NOT TESTED
CFG-AUD-001 | MOD-003 | F-007 | AC-CFG-AUD-001 | T-CFG-AUD-001 | DOC-006 | DRAFT | NOT TESTED

## MOD-001 Review
Decision ID | Requirement ID(s) | Decision Required | Proposal (NOT APPROVED) | Owner | Status
UM-DEC-001 | IAM-FR-002 | Login identifier: username, email, staff ID, SSO?: Prefer an identity independent of employee records | IT / Requestor | OPEN
UM-DEC-002 | IAM-FR-001 / IAM-FR-008 | Mandatory profile fields and editable profile fields?: Collect minimum operational information | IT / HR | OPEN
UM-DEC-003 | IAM-FR-001 / IAM-FR-006 / IAM-FR-010 | Who is allowed to bootstrap and administer the first System Admin?: Explicit privileged setup with last-admin protection | IT | OPEN
UM-DEC-004 | IAM-FR-006 / IAM-FR-007 | Role catalogue and permission matrix?: Separate account administrator from future HR permissions | IT / HR | OPEN
UM-DEC-005 | IAM-FR-004 | Password reset / invitation channel?: No assumed SMTP, SSO or external service | IT | OPEN
UM-DEC-006 | IAM-FR-003 / IAM-FR-009 | Session policy, disabled-account revocation and recovery?: Re-check authorization on protected operations | IT / Security | OPEN
UM-DEC-007 | IAM-FR-011 | Is public self-registration permitted?: Disabled until explicitly approved | IT / HR | OPEN
UM-DEC-008 | IAM-FR-005 / IAM-AUD-001 | Deactivation vs deletion and retention requirements?: Deactivate rather than erase audit history | IT / Compliance | OPEN
UM-DEC-009 | SYS-DR-001 | Must users map to employees, and when?: No mandatory employee record in System Core | HR / IT | OPEN
UM-DEC-010 | SYS-NFR-001 | Target language, keyboard and mobile requirements?: Start accessible and responsive; confirm detailed targets | Requestor / IT | OPEN
UM-DEC-011 | SYS-SEC-001 / SYS-SEC-002 | MFA, brute-force limits, rate limit and security controls?: Design least-privilege security baseline, confirm controls | IT / Security | OPEN
UM-DEC-012 | SYS-AUD-001 / IAM-AUD-001 | Audit access and retention period?: Audit privileged changes; retention awaiting policy | IT / Compliance | OPEN

## Change Requests
CR ID | Created | Action | Module ID | Requirement ID(s) | Requestor / Reason | Before | After | Impact Review | Decision | Approver | Approval Date | PR / Commit | Closure Date

## Impact Review
CR ID | Module ID | Requirement IDs | Data / Migration | Access / Security | Integration | UI / Reporting | Tests | Risk | Rollback | Reviewer | Decision | Evidence Link

## Scope Policy
Policy ID | Rule | Status
SCOPE-001 | System Core first; HR Core must await formal requirements | RECORDED
BOUNDARY-001 | MOD-001 User Management is the first planned module | RECORDED
BOUNDARY-002 | MOD-002 settings only when required and reviewed | RECORDED
BOUNDARY-003 | MOD-003 security and auditing support MOD-001 | RECORDED
BOUNDARY-004 | MOD-004..011 HR Core; do not implement without HR approval | HOLD
BOUNDARY-005 | User Account is not necessarily an Employee Record | PROPOSED DESIGN
GOV-001 | 32 requirements remain DRAFT; 0 test evidence | NOT APPROVED
GOV-002 | Use CR when actual module/requirement scope is added, changed or removed | CONTROL
GOV-003 | Update Excel, CSV and SRS together in the same PR | CONTROL